## Current
Detailed T&M Job Analysis for SMB (2165)
Current Version: | 1.3.0
Last Update: | 2011-03-16
Item Number | Description | Type (Maintenance, Enhancement, Feature) | Priority ( 1 to 5, 1 is highest) | Difficulty ( 1 to 5, 1 is most difficult) | Target Release | Date Added | Notes
5 | Fix issue where the progress bar shows up in unexpected locations on the Window | Maintenance | 5 | 3 | 2.0.0 | 2010-11-01 | Not fixed in 1.0.1 - Moved to 1.0.2
33 | Modify template so that items that are not billed that are 90 days from the final transaction date show up in RED, 30 to 89 days show up in yellow. | Enhancement | 1 | 3 | 2.0.0 | 2011-03-11 | Only in the template; this would be done with conditional formatting in Excel
37 | Put up a splash screen as the program is first loading. | Enhancement | 3 | 5 | 2.0.0 | 2011-04-14
38 | Installer has wrong icon in dialog box header | Maintenance | 3 | 5 | 2.0.0 | 2011-04-14
39 | If a record is billed; even if it is an unbillable cost code, it should be shown as billed in the template. | Maintenance | 3 | 4 | 2.1.2 | 2012-03-15 | Example: Job 30573 in APSLLC dataset
40 | Version 2.1.0 is adding an estimated billing where it did not before for non-billable records. | Maintenance | 3 | 4 | 2.1.2 | 2012-03-15 | Example: Job 60259, job cost record 575740; version 8 of the template in APSLLC dataset.
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
* | * | * | * | * | * | * | *

## Completed Items
Detailed T&M Job Analysis for SMB (2165)
Current Version: | 1.3.0
Last Update: | 2011-03-16
Item Number | Description | Type (Maintenance, Enhancement, Feature) | Priority ( 1 to 5, 1 is highest) | Difficulty ( 1 to 5, 1 is most difficult) | Target Release | Date Added | Notes | Completed Release
2 | Increase speed of report generation | Enhancement | 3 | 2 | 1.0.6 | 2010-11-01 |  | 1.1.0
3 | A searchable job control with allowance to: enter job number directly and hit enter, app verifies to job; serch by number; seacrh by name | Enhancement | 3 | 2 | 1.0.6 | 2010-11-01 | This will go into our Syscon Accounting API | 1.1.0
6 | Speed of extracting and calculating is a problem for large jobs. Testing a job with 13,000 T&M Billing Records, and I could not get it to work. | Maintenance | 1 | 2 | 1.0.6 | 2010-11-16 | Note that the core logic program (version 6) ran the same job off the same network drive and connection in just a few seconds. | 1.1.0
11 | T & M Job Types should be in numerical order | Enhancement |  |  | 1.0.6 | 2010-11-18 | ARA | 1.1.0
12 | Receiving unhandled exception errors in MB 16 | Maintenance |  |  | 1.0.6 | 2010-11-18 | ARA | 1.1.0
13 | Licensing is not disabling program with invalid license file | Maintenance |  |  | 1.0.6 | 2010-11-19 | ARA | 1.1.0
16 | switch to new syscon icon | Maintenance | 1 | 5 | 1.0.6 | 2010-12-07 |  | 1.1.0
19 | Allow multiple users running from the same EXE (like in a TS environment) | Maintenance | 1 | 3 | 1.0.6 | 2010-12-21 | LAW | 1.1.0
4 | When exporting to Excel, need to load to the named range "DetailData" | New Feature | 3 | 3 | 1.1.0 | 2010-11-01 |  | 1.1.0
7 | Initial load of program when viewing a large data set takes a long time before the primary screen appears. To the user it looks like the application has hung. Need to put up an initial splash screen and/or progress bar for loading the combo box - and, if possible, increase the speed of the load. | Maintenance | 2 | 3 | 1.1.0 | 2010-11-16 |  | 1.1.0
8 | Standardize look of the interface - font size, Syscon icon, Alt-Key to access buttons and menu items; window size; menu ribbon; standard menu format for windows (File, Edit, Help); use copyright symbol in help about; | Maintenance | 3 | 4 | 1.1.0 | 2010-11-16 |  | 1.1.0
9 | Move the "select dir" buttons to an "Options" menu item; but continue to show the current directory in the main dialog box. | Maintenance | 3 | 4 | 1.1.0 | 2010-11-16 |  | 1.1.0
14 | Progress bar while loading jobs | Enhancement | 3 | 3 | 1.1.0 | 2010-12-07 |  | 1.1.0
17 | Allow user selection of target template | New Feature | 2 | 3 | 1.1.0 | 2010-12-21 | LAW | 1.1.0
18 | Need switch to turn off logging to log.txt in the GUI | Maintenance | 2 | 4 | 1.1.0 | 2010-12-21 | LAW - This log file could get quite large. | 1.1.0
20 | Modify the template so that the "billable amount" column is only showing a value for billed items. | Enhancement | 1 | 3 | 1.1.0 | 2010-12-21 | LAW - APS request | 1.1.0
21 | Show the employee name, vendor name, or equipment name from the job cost record as a column of data. | Enhancement | 1 | 3 | 1.1.0 | 2010-12-21 | LAW - APS request | 1.1.0
24 | Job Type name is not showing when a job is selected | Maintenance | 3 | 5 | 1.1.0 | 2010-12-31 | LAW | 1.1.0
25 | Job Type Set up dialog box - resize the grid when the window is resized. | Maintenance | 3 | 5 | 1.1.0 | 2010-12-31 | LAW | 1.1.0
26 | Job Type setup dialog box - title of the job type column says "Cost Code" | Maintenance | 3 | 5 | 1.1.0 | 2010-12-31 | LAW | 1.1.0
28 | In addtion to the numbers of each of these values, show the name as well: job name, phase name, cost code name, source name, record status name, billing status name, cost type name, pay type name | Enhancement | 3 | 3 | 1.1.0 | 2011-01-07 | LAW | 1.1.0
22 | Show the billed payroll hours in the report. Currently, we show the cost hours, but not the billed hours. | Enhancement | 1 | 3 | 1.1.0 | 2010-12-21 | LAW - APS request | 1.1.0
| Installation listing in control panel should start with "Syscon ReportsPlus" | Maintenance | 3 | 5 | TBD | 2010-12-31 | LAW | 1.1.0
| Use the Syscon icon on the desktop and program files icon | Maintenance | 3 | 4 | 1.1.0 | 2010-12-31 | LAW | 1.1.0
23 | In "Options" remove all abbreviations in the menu descriptions. For example "Select MB Dir" should be "Select Master Builder Directory" | Maintenance | 3 | 5 | 1.1.1 | 2011-02-15 | ARA 03/16/11 - OK | 1.1.2
1 | Indicate a job is a T&M job by definition of the T&M job types cross-reference table. Allow a filter that shows all jobs or just T&M jobs. | Enhancement | 1 | 4 | 2.0.0 | 2010-11-01 | ARA 03/16/11 - OK | 1.1.2
15 | Any database configuration files need to be kept in the database directory so it is accessible to all users. | Enhancement | 1 | 2 | 2.0.0 | 2010-12-07 | ARA 03/16/11 - OK | 1.1.2
27 | Add totals to all numeric columns - this should be two totals, visible lines and all lines. | Enhancement | 1 | 5 | 2.0.0 | 2011-02-15 | ARA 03/16/11 - OK This is actually only in the template | 1.1.2
30 | Allow selection of multiple jobs for analysis. Allow filter of jobs by the job supervisor (actrec.sprvsr), site contact (actrec.slsemp?); job status (actrec.status) | Enhancement | 1 | 3 | 2.0.0 | 2011-03-11 | ARA 03/16/11 - OK | 1.1.2
29 | Always show billing quantities, even if not billed. | Enhancement | 1 | 5 | 2.0.0 | 2011-03-11 |  | 1.1.2
31 | Add filter for data extraction in analysis: ; job cost transaction date (jobcst.trndte) | Enhancement | 1 | 3 | 2.0.0 | 2011-03-11 |  | 1.1.2
32 | Add a column in the analysis to list the biller (actrec.estimator??) | Enhancement | 1 | 3 | 2.0.0 | 2011-03-11 |  | 1.1.2
If a non-labor job cost record has not been billed (acrinv = 0 and billing status = 1) and override has been checked, show the billing amount as the estimating billing in the T&M analysis.
| Modify the template: Create a "Pending Billed Hours" column to the immediate right of the "Billed Hours" existing column. |  |  |  | 1.3.0 | 2011-04-15
If a labor job cost records has not been billed (acrinv = 0 and billing status = 1) and there are no cost hours, then put the billing quantity in the "Pending Billed Hours" column and calculate the estimated billing from the billed quantity as hours.
34 | Allow user to enter information in user editable columns in the template. This data will ultimately be used to update Master Builder. - Allow user to mark items as non-billable - Allow user to add text notes - Allow user to mark a partial billing of billing items - Allow user to add an entire item | New Feature | 1 | 1 | 2.1.0 | 2011-03-11 | Possibly use a dialog box to pop-up in Excel to add a row with other specific items. | 2.1.0
35 | Create a process to capture that a project manager has reviewed items marked as non-billable and approves them. | New Feature | 1 | 2 | 2.0.0 | 2011-03-11 |  | 2.1.0
36 | Read a reviewed T&M analysis and update Master Builder job cost records with all required changes based on information entered in the T&M analyais. | New Feature | 1 | 1 | 2.0.0 | 2011-03-11 | - Read the file - Display a grid of recommended changes - Post the changes to Master Builder Capture the source database Confirm the job exists in the source database and is open status | 2.1.0